## Dashboard
Audit Dashboard
| Client Name | High Risk Total | Medium Risk Total | Low Risk Total
| American Airlines | 1 | 0 | 4
| American Apparel | 3 | 4 | 3
| Bass Pro Shop | 3 | 6 | 4
| Creative Energy Group | 1 | 1 | 7
| Google | 5 | 8 | 1
| Hostess | 7 | 3 | 3
| Media General | 5 | 0 | 0
| Merck | 0 | 2 | 4
| NS-LIJ Health System | 2 | 3 | 5
| Pioneer Iron & Steel | 8 | 6 | 4
| Royal Free London | 4 | 4 | 5
| Shamrock Foods | 2 | 3 | 6
| Walk Free Foundation | 5 | 0 | 2
| Wells Fargo | 6 | 4 | 0
| Grand Total | 52 | 44 | 48

## Audit Data
AUDIT DATA
Client Name | Start Date | End Date | Duration | # of Team Members | Project Budget | Actual Budget | Remainder | High Risk | Medium Risk | Low Risk | Issues | Revisions | Pending Actions
American Airlines | 2016-05-05 | 2016-07-01 | 57 | 10 | 1000000 | 880000 | 120000 | 1 | 0 | 4 | 2 | 0 | 4
NS-LIJ Health System | 2016-05-10 | 2016-08-10 | 92 | 6 | 900000 | 920000 | -20000 | 2 | 3 | 5 | 1 | 2 | 3
American Apparel | 2016-06-10 | 2017-03-01 | 264 | 4 | 860000 | 880000 | -20000 | 3 | 4 | 3 | 2 | 1 | 2
Google | 2016-06-22 | 2016-08-04 | 43 | 5 | 1000000 | 998050 | 1950 | 5 | 8 | 1 | 1 | 0 | 0
Pioneer Iron & Steel | 2016-07-14 | 2016-11-01 | 110 | 7 | 294000 | 280000 | 14000 | 8 | 6 | 4 | 0 | 3 | 1
Media General | 2016-07-14 | 2017-01-20 | 190 | 5 | 123400 | 125000 | -1600 | 5 | 0 | 0 | 2 | 0 | 2
Wells Fargo | 2016-08-01 | 2016-10-01 | 61 | 12 | 250500 | 236000 | 14500 | 6 | 4 | 0 | 1 | 2 | 3
Hostess | 2016-08-14 | 2016-08-30 | 16 | 2 | 127200 | 126000 | 1200 | 7 | 3 | 3 | 0 | 1 | 4
Merck | 2016-09-01 | 2016-12-10 | 100 | 7 | 80000 | 79900 | 100 | 0 | 2 | 4 | 1 | 3 | 2
Royal Free London | 2016-10-01 | 2016-11-15 | 45 | 5 | 77000 | 77000 | 0 | 4 | 4 | 5 | 2 | 0 | 0
Bass Pro Shop | 2016-10-01 | 2016-12-01 | 61 | 10 | 65000 | 55000 | 10000 | 3 | 6 | 4 | 3 | 2 | 0
Shamrock Foods | 2016-11-01 | 2016-12-01 | 30 | 4 | 550000 | 651000 | -101000 | 2 | 3 | 6 | 0 | 1 | 1
Creative Energy Group | 2016-11-10 | 2016-12-10 | 30 | 3 | 45000 | 42000 | 3000 | 1 | 1 | 7 | 1 | 0 | 2
Walk Free Foundation | 2016-12-01 | 2017-02-10 | 71 | 2 | 32500 | 25000 | 7500 | 5 | 0 | 2 | 2 | 1 | 3
[5 empty] | 5404600 | 5374950 | 29650 | 52 | 44 | 48 | 18 | 16 | 27